## Risk_Register
ID | Risk_Title | Description | Category | Impact | Likelihood | Score | RAG
OP-001 | Glaucoma Follow-up Backlog | Patient harm due to delayed monitoring | Clinical | 5 | 4 | 20 | Red
OP-002 | Medisoft Data Transfer Failure | Inaccurate waiting list data | Admin | 4 | 3 | 12 | Amber
OP-003 | Theatre Staffing Vacancy | Cancellation of elective lists | Workforce | 3 | 5 | 15 | Red
OP-004 | Injection Clinic Capacity | Failure to meet NICE TA intervals for AMD | Clinical | 4 | 4 | 16 | Red
OP-005 | Diagnostic Equipment Obsolescence | Breakdown of older OCT machines | Infrastructure | 3 | 3 | 9 | Amber
OP-006 | Patient DNA Rates | Inefficient use of clinic capacity | Operational | 2 | 4 | 8 | Amber
OP-007 | Wrong Site Surgery | Catastrophic surgical error | Clinical | 5 | 1 | 5 | Green
OP-008 | Budget Overspend (Locums) | Financial deficit at year-end | Finance | 3 | 4 | 12 | Amber
OP-009 | CQC Inspection Preparedness | Failure to evidence clinical audit cycle | Regulatory | 3 | 3 | 9 | Amber
OP-010 | Nursing Sickness | Impact on clinic and ward safety | Workforce | 3 | 4 | 12 | Amber